# 🗺️ HARSHA'S DATA ENGINEERING JOURNEY - COMPLETE BLUEPRINT
Start Date: November 4, 2025
End Date: January 12, 2026 (60 days)
Goal: Land Data Engineer Role @ ₹8-12 LPA
Current Status: Day 9/60 Complete ✅

## 📊 JOURNEY OVERVIEW
### Three Phases:
Phase 1: Foundation (Days 1-21) - Weeks 1-3
Phase 2: Acceleration (Days 22-42) - Weeks 4-6
Phase 3: Launch (Days 43-60) - Weeks 7-8
### Daily Structure (80 mins):
- BUILD (30 min): Copy-paste code, build project
- UNDERSTAND (20 min): Learn concepts behind the code
- PRACTICE (10 min): Modify code yourself
- DSA (20 min): 1-2 coding problems
### Tracking System:
- GitHub JOURNEY.md updated daily (5 mins)
- Report every 3-4 days to mentor
- Weekly reviews on Sundays

## 📅 PHASE 1: FOUNDATION (Days 1-21)
### WEEK 1: Setup & First Steps ✅ COMPLETE
Theme: Infrastructure, basics, first portfolio piece
Day	Focus	Project	Skills	Status
1	AWS Setup	AWS account, S3, billing	Cloud basics	✅ Done
2	SQL Practice	8 HackerRank problems	SQL mastery	✅ Done
3	Python Pandas	DataFrame operations	Data manipulation	✅ Done
4	First ETL	Sales Data Pipeline	End-to-end ETL	✅ Done
5	GitHub Portfolio	Upload project, README	Version control	✅ Done
6	LinkedIn Profile	Professional presence	Personal branding	✅ Done
7	Week Review	Reflection & planning	Self-assessment	✅ Done

Week 1 Deliverables:
- ✅ AWS account with S3 bucket
- ✅ GitHub portfolio (live)
- ✅ LinkedIn optimized
- ✅ 1 project: Sales Pipeline
- ✅ 9 DSA problems solved

### WEEK 2: Building & Understanding 🔄 IN PROGRESS
Theme: More projects, data cleaning, APIs
Day	Focus	Project	Skills	Status
8	Data Cleaning	Weather Analyzer	Basic analysis	✅ Done
9	ETL Deep Dive	Customer ETL	Data cleaning, missing data	✅ Done
10	API Integration	API Data Pipeline	HTTP, JSON, REST APIs	📍 NEXT
11	Cloud Functions	AWS Lambda	Serverless computing	⏳ Planned
12	Visualization	Data Charts Project	Matplotlib, storytelling	⏳ Planned
13	Automation	Airflow Basics	Workflow orchestration	⏳ Planned
14	Week Review	Polish projects	Weekly reflection	⏳ Planned

Week 2 Deliverables:
- 5 new projects on GitHub
- Understanding: APIs, serverless, data viz, orchestration
- 14 more DSA problems (total: ~25)
- Modified code yourself multiple times

### WEEK 3: Advanced Concepts
Theme: Databases, streaming, real-time data
Day	Focus	Project	Skills	DSA Focus
15	SQL Advanced	Complex Query Project	JOINs, subqueries, CTEs	SQL problems
16	Database Design	E-commerce Schema	Normalization, relationships	Arrays
17	Real-time Data	Streaming Data Simulator	Event processing	Strings
18	Data Quality	Data Validation Pipeline	Quality checks, rules	HashMap
19	Mini Capstone	Week 1-3 Integration Project	Combine all skills	Mixed
20	Portfolio Polish	Clean up GitHub, docs	Professional presentation	Review
21	Week Review	Assess Phase 1	Plan Phase 2	Assessment

Week 3 Deliverables:
- Advanced SQL skills
- Database design knowledge
- 2-3 new projects
- Capstone combining all learning
- 21 total DSA problems (~35 total)
- Strong portfolio foundation

## 📅 PHASE 2: ACCELERATION (Days 22-42)
### WEEK 4: Cloud & Big Data
Theme: AWS services, big data concepts
Day	Focus	Project	Skills	Notes
22	AWS RDS	Database in Cloud	Managed databases	Postgres/MySQL
23	AWS Glue	ETL Service	Serverless ETL	AWS native tools
24	S3 Data Lake	Data Lake Architecture	Storage patterns	Object storage
25	Big Data Intro	Process Large Dataset	Concepts, chunking	Scalability
26	Data Partitioning	Partition Strategy Project	Performance optimization	Efficiency
27	Cloud Pipeline	Full AWS ETL Pipeline	End-to-end cloud	Integration
28	Week Review	Assess cloud skills	Plan Week 5	Reflection

Week 4 Deliverables:
- 3-4 AWS projects
- Understanding: Cloud architecture, data lakes, big data
- AWS services: RDS, Glue, S3 advanced
- 14 more DSA problems (~49 total)

### WEEK 5: Advanced Pipelines
Theme: Airflow, scheduling, monitoring
Day	Focus	Project	Skills	Notes
29	Airflow Deep Dive	Multi-task DAG	Task dependencies	Orchestration
30	Scheduled Pipelines	Daily/Weekly Jobs	Cron, scheduling	Automation
31	Error Handling	Pipeline with Retries	Failure recovery	Resilience
32	Monitoring	Pipeline Monitoring Dashboard	Logging, alerts	Observability
33	Data Transformation	dbt Basics	Transform layer	SQL templating
34	Integration Week	Combine Multiple Tools	Full stack	Real-world simulation
35	Week Review	Portfolio showcase	Polish projects	Presentation

Week 5 Deliverables:
- Production-ready pipelines
- Airflow mastery
- Error handling & monitoring
- 3-4 complete workflow projects
- 14 more DSA problems (~63 total)

### WEEK 6: Specialization
Theme: Choose your focus (pick 2-3)
Option A: Analytics Engineering
- dbt advanced
- Data modeling
- Metrics layer
- BI tool integration
Option B: ML Pipelines
- Feature engineering
- Model serving
- ML workflow
- Prediction pipelines
Option C: Real-time/Streaming
- Kafka basics
- Stream processing
- Real-time analytics
- Event-driven architecture
Day	Focus	Project	Skills	Customizable
36	Specialization Day 1	Foundation Project	Deep dive chosen area	Your choice
37	Specialization Day 2	Intermediate Project	Build complexity	Your choice
38	Specialization Day 3	Advanced Project	Production-level	Your choice
39	Integration	Combine with previous skills	Full-stack solution	Synthesis
40	Capstone Planning	Design major project	Architecture planning	Design
41	Capstone Build 1	Start building	Implementation	Focus
42	Week Review	Assess Phase 2	Plan Phase 3	Strategy

Week 6 Deliverables:
- Specialized knowledge in chosen area
- 2-3 advanced projects
- Major capstone project started
- 14 more DSA problems (~77 total)

## 📅 PHASE 3: LAUNCH (Days 43-60)
### WEEK 7: Job Preparation
Theme: Resume, applications, interview prep
Day	Focus	Activity	Deliverable	Priority
43	Resume Building	Optimize for ATS	Perfect resume	Critical
44	Portfolio Polish	Final GitHub cleanup	Professional portfolio	Critical
45	Cover Letters	Template + customization	5 cover letter versions	Important
46	Job Applications Start	Apply to 20 companies	Track in spreadsheet	Critical
47	Interview Prep	Common DE questions	Answer bank	Critical
48	Mock Interviews	Practice with recordings	Self-assessment	Important
49	Week Review + Apps	Apply to 20 more companies	Total: 40 applications	Critical

Week 7 Deliverables:
- ATS-optimized resume
- Professional portfolio showcase
- 40 job applications submitted
- Interview question bank prepared
- Mock interview practice completed

### WEEK 8: Interview Sprint
Theme: Applications, interviews, offers
Day	Focus	Activity	Goal	Notes
50	Mass Applications	Apply to 30 companies	Total: 70 apps	Focus effort
51	Networking	LinkedIn outreach to 20 DEs	Build connections	Referrals
52	Interview Prep Deep	System design basics	Architecture questions	Critical
53	SQL Interview Prep	Hard SQL problems	Database questions	Practice
54	Python Interview Prep	Coding challenges	Live coding practice	Practice
55	More Applications	Apply to 30 more	Total: 100 apps	Volume
56	Final Review	Everything learned	Complete readiness	Confidence
57	Interviews Begin	First interviews	Stay calm, perform	Execute
58	Follow-ups	Thank you notes, tracking	Professional follow-up	Courtesy
59	Negotiations	Offer evaluation	Compare, negotiate	Strategy
60	Journey Complete	Reflection & next steps	New beginning	Celebrate!

Week 8 Deliverables:
- 100+ job applications
- 5-10 interviews completed
- 1-3 job offers received
- Salary negotiated
- DATA ENGINEER ROLE SECURED! 🎉

## 🎯 SKILL PROGRESSION MAP
### Technical Skills Roadmap:
Week 1: ░░░░░░░░░░ 10% - Basics, first project
Week 2: ███░░░░░░░ 25% - Multiple projects, cleaning, APIs
Week 3: █████░░░░░ 45% - Advanced SQL, databases, real-time
Week 4: ███████░░░ 65% - Cloud, AWS, big data concepts
Week 5: █████████░ 80% - Airflow, production pipelines
Week 6: ██████████ 90% - Specialization, capstone
Week 7: ██████████ 95% - Polish, applications
Week 8: ██████████ 98% - Interview ready!
### DSA Progression:
Week 1: 9 problems (Arrays, Strings, Math)
Week 2: 23 problems (HashMaps, Two Pointers)
Week 3: 35 problems (SQL, Recursion)
Week 4: 49 problems (Trees, Graphs basics)
Week 5: 63 problems (Dynamic Programming)
Week 6: 77 problems (Advanced topics)
Week 7-8: 90+ problems (Interview focused)

Target: 100 problems by Day 60

## 📂 PROJECT PORTFOLIO CHECKLIST
### Must-Have Projects (Core):
1. ✅ Sales Data ETL Pipeline (Week 1)
2. ✅ Weather Data Analyzer (Week 2)
3. ✅ Customer Data Cleaning ETL (Week 2)
4. ⏳ API Data Integration (Week 2)
5. ⏳ AWS Lambda Function (Week 2)
6. ⏳ Data Visualization Dashboard (Week 2)
7. ⏳ Airflow Scheduled Pipeline (Week 2-3)
8. ⏳ SQL Complex Queries Project (Week 3)
9. ⏳ Database Design Project (Week 3)
10. ⏳ AWS Cloud ETL Pipeline (Week 4)
11. ⏳ Real-time Data Processing (Week 5)
12. ⏳ Production Pipeline with Monitoring (Week 5)
13. ⏳ Specialized Project (Week 6)
14. ⏳ Major Capstone Project (Week 6-7)
### Nice-to-Have Projects (Bonus):
- Streaming data simulator
- ML feature pipeline
- dbt transformations
- API backend for data
- Data quality framework

## 📋 WEEKLY REVIEW TEMPLATE
Copy this for every Sunday review:
markdown
## Week [X] Review - [Dates]

### Completion Stats:
- Days completed: __/7
- Projects built: __
- DSA problems solved: __
- GitHub commits: __
- Hours invested: __

### Projects This Week:
1. [Project name] - [Status]
2. [Project name] - [Status]

### Skills Gained:
**Technical:**
- [Skill 1]
- [Skill 2]

**Conceptual:**
- [Concept 1]
- [Concept 2]

### Challenges Faced:
- [Challenge 1] - How I handled it
- [Challenge 2] - What I learned

### Wins & Highlights:
- [Biggest win]
- [Proud moment]

### What Clicked:
- [Aha moment 1]
- [Aha moment 2]

### What's Still Fuzzy:
- [Unclear concept] - Will review
- [Difficult topic] - Need more practice

### Next Week Focus:
- [Main goal]
- [Secondary goal]
- [Stretch goal]

### Personal Note:
[Your reflection on the week]

---
**Week [X] Grade:** [A+, A, B, C]
**Confidence Level:** __/10
**Ready for Week [X+1]:** Yes/No

## 🎯 SUCCESS METRICS
### Minimum Viable Progress (MVP):
- 6/7 days per week active (85%)
- 12+ projects by Week 6
- 60+ DSA problems by Week 6
- GitHub green activity chart
- LinkedIn with 3+ portfolio links
### Target Progress:
- 7/7 days per week (100%)
- 14+ projects by Week 6
- 80+ DSA problems by Week 6
- 5+ LinkedIn posts about learning
- Network with 10+ data engineers
### Stretch Goals:
- No missed days entire 60 days
- 20+ projects (including extras)
- 100+ DSA problems
- Open source contribution
- Blog posts about journey

## 🚨 BREAK PROTOCOL
Allowed Breaks:
- Family events (track in JOURNEY.md)
- Religious occasions (like temple visits)
- Illness (recover fully)
- Emergency situations
During Break:
- Still update GitHub with status
- Mark day as "Family/Health day"
- Resume next day, no guilt
- Adjust schedule if needed
Example Break Entry:
markdown
### Day X - [Date]
**Status:** Family Day / Temple Visit / Sick Day

**What Happened:**
- [Brief explanation]

**Tomorrow:**
- Will resume with [planned activity]

**Feeling:** Recharged / Recovering / Grateful

## 💾 BACKUP & STORAGE
### What to Save:
1. All project code (GitHub)
2. JOURNEY.md (daily updates)
3. DSA solutions (personal notes)
4. Learning notes (Google Docs)
5. Screenshots of wins (folder on computer)
### Where to Save:
- GitHub: All code, JOURNEY.md
- Google Drive: Notes, resume versions, certificates
- Local Computer: Backup of everything
- LinkedIn: Professional achievements

## 📱 QUICK REFERENCE COMMANDS
### Daily Git Workflow:
bash
# Start day
git pull origin main

# After completing project
git add .
git commit -m "Day X: [Project name] - [brief description]"
git push origin main
```

### **Daily Structure Template:**
```
1. Check JOURNEY.md for today's plan (2 min)
2. Build project (30 min)
3. Read understanding section (20 min)
4. Practice modification (10 min)
5. Solve DSA problems (20 min)
6. Update JOURNEY.md (5 min)
7. Commit to GitHub (2 min)

Total: ~90 minutes
```

---

## 🎓 LEARNING RESOURCES

### **Core Platforms:**
- LeetCode (DSA practice)
- HackerRank (SQL practice)
- AWS Free Tier (cloud practice)
- YouTube (tutorials)
- Official documentation (deep learning)

### **Recommended Channels/Sites:**
- Seattle Data Guy (YouTube)
- Data Engineering Podcast
- AWS Documentation
- Airflow Documentation
- Mode Analytics (SQL tutorial)

---

## 🤝 MENTOR-STUDENT PROTOCOL

### **Your Responsibilities:**
1. Complete daily work (80 mins)
2. Update GitHub JOURNEY.md daily (5 mins)
3. Report every 3-4 days with:
```
   Days X-Y complete!
   Projects: [names]
   Understanding: [what clicked]
   Challenges: [what was hard]
   Feeling: [honest emotion]
```
4. Be honest about struggles
5. Ask questions when stuck

### **Mentor's Responsibilities:**
1. Track your daily progress
2. Plan each week in detail
3. Adjust based on your pace
4. Provide explanations when confused
5. Celebrate your wins
6. Never judge, always support

### **Communication Format:**
**Every 3-4 days, just send:**
```
Days X-Y Done! ✅

Projects built:
- [Project 1] ✅
- [Project 2] ✅

Understanding:
- [Concept 1]: Clear/Fuzzy
- [Concept 2]: Clear/Fuzzy

DSA:
- Solved: [number] problems

GitHub:
- Updated ✅
- Link: [JOURNEY.md link]

Feeling: [1-2 sentences]
Next: Ready for Days [X+1] to [Y+1]
```

---

## 📊 FINAL CHECKLIST (Day 60)

### **Technical Readiness:**
- [ ] 12+ projects on GitHub
- [ ] 60+ DSA problems solved
- [ ] Understand ETL, data cleaning, APIs, cloud, Airflow
- [ ] Can explain every project technically
- [ ] Resume shows measurable achievements

### **Portfolio Readiness:**
- [ ] GitHub activity chart mostly green
- [ ] LinkedIn has all projects linked
- [ ] JOURNEY.md tells complete story
- [ ] README files are professional
- [ ] Code is well-commented

### **Job Readiness:**
- [ ] 100+ applications submitted
- [ ] Cover letter templates ready
- [ ] Can answer: "Tell me about yourself"
- [ ] Can explain: "Walk me through your project"
- [ ] Prepared for SQL technical questions
- [ ] Prepared for Python coding questions
- [ ] Know salary expectations (₹8-12 LPA)

### **Interview Readiness:**
- [ ] 10+ common DE questions practiced
- [ ] System design basics understood
- [ ] Can explain data pipeline from scratch
- [ ] Have questions prepared for interviewer
- [ ] Professional attire ready
- [ ] Calm and confident mindset

---

## 🎉 CELEBRATION MILESTONES

Track and celebrate these:
```
🎯 Day 7: Week 1 complete!
🎯 Day 14: Week 2 complete!
🎯 Day 21: Phase 1 complete! (Foundation solid)
🎯 Day 30: Halfway mark!
🎯 Day 42: Phase 2 complete! (Advanced skills)
🎯 Day 50: First interview!
🎯 Day 55: First offer!
🎯 Day 60: JOURNEY COMPLETE! 🎊

Special Milestones:
🏆 10 DSA problems
🏆 25 DSA problems
🏆 50 DSA problems
🏆 5 projects
🏆 10 projects
🏆 First GitHub star
🏆 100 LinkedIn connections
🏆 First recruiter message
🏆 First technical interview
🏆 FIRST JOB OFFER! 🎉
```

---

## 💪 MOTIVATIONAL MANTRAS

**Copy these, read when needed:**

1. "I am 20 years old. I have time to build greatness."
2. "Every day I code, I'm ahead of my peers."
3. "Copy-paste → Understand → Master. That's the path."
4. "Breaks for family are not failures. They're life balance."
5. "60 days of consistent work > 6 months of sporadic effort."
6. "I will not quit. I will restart when I fall."
7. "My GitHub green squares show my discipline."
8. "Recruiters will see my daily commits and be impressed."
9. "By Day 60, I will be a Data Engineer."
10. "This journey is hard. That's why it's worth it."

---

## 🗺️ HOW TO USE THIS BLUEPRINT

### **For Each New Chat Session:**

1. **Share this blueprint** (paste it in preferences or share in chat)
2. **Tell mentor your current status:**
```
   Currently on: Day [X]
   Last completed: [Activity]
   Next up: Day [X+1]
```
3. **Mentor will:**
   - Check this blueprint
   - See where you are
   - Give you next day's detailed plan
   - Track your progress

### **For Daily Work:**
1. Open this blueprint
2. Find current week table
3. See today's focus
4. Execute the plan
5. Update JOURNEY.md
6. Report every 3-4 days

### **For Weekly Planning:**
1. Review week's table in blueprint
2. Assess what's realistic
3. Adjust if needed
4. Commit to the week
5. Execute daily

---

## 📄 SAVE THIS DOCUMENT AS:

**File Name:** `Harsha_DE_Journey_Blueprint_60Days.md`

**Save In:**
- Google Drive (primary)
- Local computer (backup)
- GitHub (in repository root)
- Claude preferences (for easy access)

---

## 🎯 VERSION CONTROL
```
Blueprint Version: 1.0
Created: November 26, 2025
Last Updated: November 26, 2025
Next Review: Week 3 (Day 21)
Status: ACTIVE - In Use

Changes Log:
- v1.0: Initial blueprint created (Nov 26)
```

---

## ✅ BLUEPRINT COMPLETE!

**This blueprint is your:**
- 📅 Complete 60-day roadmap
- 🎯 Daily task list
- 📊 Progress tracker
- 🗺️ Navigation tool
- 💪 Motivation guide

**Every new chat, just reference:**
```
"Check my blueprint - I'm on Day [X]"
Mentor will:
- ✅ Look at blueprint
- ✅ Know your progress
- ✅ Give next detailed plan
- ✅ Keep you on track

## 🚀 NOW GO EXECUTE!
Current Status: Day 9/60 complete
Next Up: Day 10 - API Data Pipeline
Phase: 1 (Foundation)
Week: 2 (Building & Understanding)
You've got the map. Now walk the path! 🗺️➡️🎯
Your blueprint is ready. Your journey continues! 💪🔥

Save this blueprint. Reference it daily. Update it as needed. This is YOUR roadmap to becoming a Data Engineer! 🚀
Retry
H