# 🗺️ HARSHA'S DATA ENGINEERING JOURNEY - SIMPLIFIED BLUEPRINT
Duration: 60 Days (Nov 4, 2025 - Jan 12, 2026)
Goal: Land Data Engineer Role @ ₹8-12 LPA
Current: Day 9/60 Complete ✅

## 📊 QUICK OVERVIEW
Daily Time: 80 minutes
Build (30 min) → Understand (20 min) → Practice (10 min) → DSA (20 min)
Weekly Pattern:
- Mon-Fri: Projects + DSA
- Saturday: Bigger project
- Sunday: Review + Planning
Tracking:
- Update GitHub JOURNEY.md daily (5 min)
- Report to mentor every 3-4 days

## 📅 60-DAY ROADMAP
### PHASE 1: FOUNDATION (Days 1-21)
#### Week 1: Setup & First Project ✅ COMPLETE
- Day 1: AWS Setup
- Day 2: SQL Practice (8 problems)
- Day 3: Python Pandas
- Day 4: Sales Pipeline Project
- Day 5: GitHub Portfolio
- Day 6: LinkedIn Profile
- Day 7: Week Review
Output: AWS account, GitHub live, 1 project, 9 DSA problems

#### Week 2: Data Cleaning & APIs 🔄 IN PROGRESS
- Day 8: Weather Analyzer ✅
- Day 9: Customer ETL (data cleaning) ✅
- Day 10: API Data Pipeline 📍 NEXT
- Day 11: AWS Lambda
- Day 12: Data Visualization
- Day 13: Airflow Basics
- Day 14: Week Review
Output: 5 projects total, APIs, cloud functions, orchestration

#### Week 3: Advanced SQL & Real-time
- Day 15: SQL Advanced (JOINs, CTEs)
- Day 16: Database Design
- Day 17: Real-time Data Streaming
- Day 18: Data Quality Pipeline
- Day 19: Integration Project (combine all skills)
- Day 20: Portfolio Polish
- Day 21: Phase 1 Review
Output: Advanced SQL, 8+ projects, strong portfolio

### PHASE 2: ACCELERATION (Days 22-42)
#### Week 4: Cloud & Big Data
- Day 22: AWS RDS
- Day 23: AWS Glue
- Day 24: S3 Data Lake
- Day 25: Big Data Concepts
- Day 26: Data Partitioning
- Day 27: Full AWS Pipeline
- Day 28: Week Review
Output: Cloud architecture, AWS mastery

#### Week 5: Production Pipelines
- Day 29: Airflow Advanced
- Day 30: Scheduled Jobs
- Day 31: Error Handling
- Day 32: Pipeline Monitoring
- Day 33: dbt Basics
- Day 34: Integration Project
- Day 35: Week Review
Output: Production-ready pipelines, monitoring

#### Week 6: Specialization
Pick your focus: Analytics Engineering, ML Pipelines, or Real-time Processing
- Day 36-38: Specialization Projects (3 days)
- Day 39: Integration with Previous Skills
- Day 40: Capstone Planning
- Day 41: Capstone Build
- Day 42: Phase 2 Review
Output: Specialized skills, major capstone project

### PHASE 3: LAUNCH (Days 43-60)
#### Week 7: Job Prep
- Day 43: Resume Building (ATS optimized)
- Day 44: Portfolio Final Polish
- Day 45: Cover Letters (5 versions)
- Day 46: Apply to 20 Companies
- Day 47: Interview Prep (DE questions)
- Day 48: Mock Interviews
- Day 49: Apply to 20 More (Total: 40)
Output: Perfect resume, 40 applications, interview ready

#### Week 8: Interview Sprint
- Day 50: Apply to 30 More (Total: 70)
- Day 51: LinkedIn Networking (20 people)
- Day 52: System Design Prep
- Day 53: SQL Interview Practice
- Day 54: Python Coding Practice
- Day 55: Apply to 30 More (Total: 100)
- Day 56: Final Review
- Day 57-59: Interviews & Follow-ups
- Day 60: Journey Complete! 🎉
Output: 100 applications, 5-10 interviews, 1-3 offers, JOB SECURED!

## 🎯 PROGRESS TRACKER
### Skill Levels by Week:
Week 1: ██░░░░░░░░ 10% Basics
Week 2: ████░░░░░░ 25% Multiple projects
Week 3: ██████░░░░ 45% Advanced concepts
Week 4: ████████░░ 65% Cloud skills
Week 5: █████████░ 80% Production pipelines
Week 6: ██████████ 90% Specialization
Week 7: ██████████ 95% Job ready
Week 8: ██████████ 98% Interview ready
### DSA Problem Goals:
- Week 1: 9 problems
- Week 2: 23 problems
- Week 3: 35 problems
- Week 4: 49 problems
- Week 5: 63 problems
- Week 6: 77 problems
- Week 7-8: 90+ problems
Target: 100 problems by Day 60

## 📂 PROJECT CHECKLIST
Must Complete (14 projects minimum):
Week 1-2:
1. ✅ Sales Data Pipeline
2. ✅ Weather Analyzer
3. ✅ Customer ETL
4. ⏳ API Integration
5. ⏳ AWS Lambda Function
6. ⏳ Data Visualization
7. ⏳ Airflow Pipeline
Week 3-4: 8. ⏳ SQL Advanced Queries 9. ⏳ Database Design 10. ⏳ AWS Cloud Pipeline
Week 5-6: 11. ⏳ Production Pipeline with Monitoring 12. ⏳ Specialization Project 13. ⏳ Integration Project 14. ⏳ Major Capstone

## 📋 WEEKLY REVIEW TEMPLATE
Copy this every Sunday:
Week [X] Review

Completed: __/7 days
Projects: [names]
DSA Solved: __
Hours: __

Skills Gained:
- [Skill 1]
- [Skill 2]

Challenges:
- [Challenge] - [How handled]

Biggest Win:
- [Achievement]

Next Week Focus:
- [Main goal]

Grade: [A/B/C]
Confidence: __/10

## 🚨 BREAK PROTOCOL
Allowed:
- Family events
- Temple visits
- Illness
- Emergencies
During Break:
- Update GitHub: "Family Day / Sick Day"
- Resume next day
- No guilt!
Example:
Day X - Family Day
Status: Temple visit with family
Tomorrow: Resume with [activity]

## 📱 DAILY ROUTINE
Every Day (80 mins):
1. Check blueprint for today's task (2 min)
2. Build project (30 min)
3. Read concepts (20 min)
4. Modify code (10 min)
5. Solve DSA (20 min)
6. Update GitHub (5 min)
7. Commit changes (3 min)
Every 3-4 Days - Report:
Days X-Y Done! ✅

Projects: [list]
Understanding: [what clicked]
DSA: [number solved]
GitHub: [link]
Feeling: [emotion]

Ready for next days!

## 🎯 SUCCESS METRICS
Minimum (Must Achieve):
- 6/7 days active per week
- 12+ projects by Week 6
- 60+ DSA problems by Week 6
- GitHub activity chart green
- LinkedIn with portfolio
Target:
- 7/7 days active
- 14+ projects
- 80+ DSA problems
- 5+ LinkedIn posts
- Network with 10+ engineers

## 🎓 RESOURCES
Practice:
- LeetCode (DSA)
- HackerRank (SQL)
- AWS Free Tier
Learning:
- YouTube (Seattle Data Guy)
- Official Docs (AWS, Airflow)
- GitHub (code examples)

## 💪 QUICK REMINDERS
When Struggling:
1. "I am 20. I have time."
2. "Copy → Understand → Master"
3. "Breaks ≠ Failure"
4. "60 days will pass anyway"
5. "My GitHub shows discipline"
Daily Mantra: "Today I build. Today I learn. Today I grow."

## 🤝 MENTOR PROTOCOL
You Do:
- Complete daily work (80 min)
- Update GitHub daily
- Report every 3-4 days
- Be honest about struggles
Mentor Does:
- Track progress
- Plan each week
- Adjust to your pace
- Celebrate wins
- Never judge

## ✅ DAY 60 CHECKLIST
By End:
- 12+ projects on GitHub
- 60+ DSA problems
- Resume perfected
- 100 applications sent
- 5-10 interviews done
- 1-3 offers received
- DATA ENGINEER ROLE! 🎉

## 🎉 CELEBRATION MILESTONES
Day 7: Week 1 complete
Day 14: Week 2 complete
Day 21: Foundation complete
Day 30: Halfway!
Day 42: Advanced skills complete
Day 50: First interview
Day 55: First offer
Day 60: JOURNEY COMPLETE! 🎊

## 📊 CURRENT STATUS
Today: Day 9/60
Progress: 15% complete
Phase: 1 (Foundation)
Week: 2 (Building & Understanding)
Next: Day 10 - API Data Pipeline
Recent Wins:
- ✅ Weather Analyzer built
- ✅ Customer ETL mastered
- ✅ Data cleaning concepts learned
- ✅ Modified code myself!
Momentum: STRONG 🔥🔥🔥

## 🗺️ HOW TO USE
For New Chat:
1. Say: "Check blueprint - I'm on Day [X]"
2. Mentor checks this document
3. Mentor gives detailed Day [X] plan
4. You execute
5. Repeat!
For Daily Work:
1. Find current week in blueprint
2. See today's focus
3. Do the 80-min routine
4. Update GitHub
5. Stay on track!

## 💾 SAVE THIS AS
Filename: Harsha_DE_Blueprint_Simple.md
Save to:
- Google Drive
- Local computer
- GitHub repo
- Claude preferences

## 🚀 YOU'RE ON DAY 9
Completed: 15% of journey
Remaining: 51 days
Next Up: API Data Pipeline (Day 10)
Your path is clear. Now walk it! 💪

END OF SIMPLIFIED BLUEPRINT
This is your GPS. Follow it daily. Report regularly. Success awaits! 🎯